## Full List
Enter Acceptance Date and Due Dates will be calculated by number of days entered in Due Date Column. Enter number of days to close escrow and COE date will be calculated. You may tab between fields or mouse over area and click to change information in a cell. | RPA-CA TRANSACTION TIMELINE WORKSHEET TT170330
Property Address:
Agent Name:
Representing:
Acceptance Date (mm/dd/yyyy):
| Number of days to close escrow: |  |  |  | COE Date: | 0
| Item/Action Description | Due Date (# of Days) |  | Scheduled Contingency Expiration | Date Provided / Ordered | Date Received | Provided by
IMMEDIATELY UPON RPA EXECUTION:
| Fill out Sales Cover Sheet | 1 |  |  |  |  | Listing Agent
| Fill out Teaming agreement |  | 1 |  |  |  | Listing Agent
| Email all RPA docs, sales cover sheet and teaming agreement to TC and Janice | 1 |  |  |  |  | Listing Agent
| Develop Escrow Summary Timeline | [5 empty] | Listing Agent
| Email to TC for their agreement on timeline | [5 empty] | Listing Agent
| Email to other agent fo their agreement | [5 empty] | Listing Agent
| Email timeline to escrow to ensure they agree on close date | [5 empty] | Listing Agent
| Printout and tape timeline to outside of escrow folder | [5 empty] | Listing Agent
| Email to client and review with them, suggest they tape it to their wall for reference | [5 empty] | Listing Agent
| Order Home Inspection, inform TC and Buyer immediately | [5 empty] | Listing Agent
Seller Provided Disclosures and Reports:
| Escrow Opened | 3 |  | 1900-01-02 |  |  | Listing Agent
| Submit HOA Information Request (If Applicable) | 3 |  | 1900-01-02 |  |  | Escrow
| MLS Agent Detail Printout - signed by Seller | 3 |  | 1900-01-02 |  |  | Listing Agent
| Representative Capacity Signature Disclosure (Seller) - RCSD-S | 3 |  | 1900-01-02 |  |  | Listing Agent
| Affiliated Business Arrangement Disclosure | 3 |  | 1900-01-02 |  |  | Listing Agent
| Transfer Disclosure Statement (TDS-11) | 7 |  | 1900-01-06 |  |  | Listing Agent
| Seller Property Questionnaire (SPQ) | 7 |  | 1900-01-06 |  |  | Listing Agent
| Exempt Seller Disclosures - ESD (if no SPQ) | 7 |  | 1900-01-06 |  |  | Listing Agent
| FIRPTA, QS (Qualified Substiture from Escrow) | 7 |  | 1900-01-06 |  |  | Listing Agent
| Go over Net Sheet with Seller | 7 |  | 1900-01-06
| Home Owners Assoc. Documents & CCR's | 7 |  | 1900-01-06 |  |  | Escrow
| Preliminary Title Report | 7 |  | 1900-01-06 |  |  | Escrow
| Wood Destroying Pest Inspection Report (if applicable) | 7 |  | 1900-01-06 |  |  | Listing Agent
| Natural Hazard Disclosure (NHD) | 7 |  | 1900-01-06 |  |  | Listing Agent
| Earthquake Guide Book & Energy Rating Pamphlet | 7 |  | 1900-01-06 |  |  | Listing Agent
| Residential Earthquake Questionnaire (pre-1960) | 7 |  | 1900-01-06 |  |  | Listing Agent
| Water Heater/Smoke Detector Statement (WHSD) | 7 |  | 1900-01-06 |  |  | Listing Agent
| Water Conserving/Monoxide Notice (WCMD) | 7 |  | 1900-01-06 |  |  | Listing Agent
| Lead Paint Notification,pre-1978 (FLD) (if applicable) | 7 |  | 1900-01-06 |  |  | Listing Agent
| Termite Pest Report (if applicable) | 7 |  | 1900-01-06 |  |  | Listing Agent
| Home Warranty | 17 |  | 1900-01-16 |  |  | Listing Agent
Buyer Contingency Items (if applicable):
| Verification of Funds to Close | 3 |  | 1900-01-02 |  |  | Buyers Agent
| HOA Common Interest Disclosures | 7 |  | 1900-01-06 |  |  | Listing Agent
| Appraisal Contingency Removal (if applicable) | 17 |  | 1900-01-16 |  |  | Both Agents
| Loan Contingency Removal (if applicable) | 21 |  | 1900-01-20 |  |  | Both Agents
| Inspections Contingency Removal (CR) | 17 |  | 1900-01-16 |  |  | Both Agents
| Home Inspection Report | 17 |  | 1900-01-16 |  |  | Buyers Agent
| Request for Repairs & Sellers Response - RR & RRRR | 17 |  | 1900-01-16 |  |  | Buyers Agent
Buyer MUST Approve, Sign and Release the Following Disclosures:
| Purchase Contract (fully signed) | 3 |  | 1900-01-02 |  |  | Both Agents
| Buyer Representation Agreement (BRNN,BRE,or BRNE) | 3 |  | 1900-01-02 |  |  | Buyers Agent
| Representative Capacity Signature Disclosure (Buyer) - RCSD-B | 3 |  | 1900-01-02 |  |  | Buyers Agent
| FHA/VA Notice and Addendum - FVA | 3 |  | 1900-01-02 |  |  | Buyers Agent
| FHA/VA Amendatory Clause - FHA/VA | 17 |  | 1900-01-16 |  |  | Buyers Agent
| Receipt for Deposit | 3 |  | 1900-01-02 |  |  | Escrow
| Counter Offers 1,2,3 (Fully Signed) | 3 |  | 1900-01-02 |  |  | Both Agents
| Addendums 1,2,3 | 3 |  | 1900-01-02 |  |  | Both Agents
| Agency Disclosure (Buyers Agent) | with Offer |  |  |  |  | Buyers Agent
| Market Conditions Advisory (MCA) | 3 |  | 1900-01-02 |  |  | Buyers Agent
| Affiliated Business Arrangement Disclosure (for BDH) | 3 |  | 1900-01-02 |  |  | Both Agents
| Buyers Inspection Advisory | with Offer |  |  |  |  | Buyers Agent
| Ensure Appraisal is Scheduled | 7 |  | 1900-01-06 |  |  | Buyers Agent
| Transfer Disclosure Statement (TDS) | 17 |  | 1900-01-16 |  |  | Buyers Agent
| Statewide Buyer & Seller Advisory (SBSA) | 17 |  | 1900-01-16 |  |  | Both Agents
| Seller Property Questionnaire (SPQ) | 17 |  | 1900-01-16 |  |  | Both Agents
| Exempt Seller Disclosures - ESD (if no SPQ) | 17 |  | 1900-01-16 |  |  | Buyers Agent
| Agent Visual Inspection Disclosure - AVID | 7 |  | 1900-01-06 |  |  | Both Agents
| Leased/liened Items Disclosure | 7 |  | 1900-01-06 |  |  | Buyers Agent
| Home Owner Association Documents (approval) | 17 |  | 1900-01-16 |  |  | Escrow
| Preliminary Title Report | 17 |  | 1900-01-16 |  |  | Escrow
| NHD & Tax/Mello-Roos page (if applicable) - receipt | 17 |  | 1900-01-16 |  |  | Buyers Agent
| Earthquake Guide Book (receipt) | 17 |  | 1900-01-16 |  |  | Buyers Agent
| Water Heater/Smoke Detector Statement (WHSD) | 17 |  | 1900-01-16 |  |  | Buyers Agent
| Water Conserving/Monoxide Notice (WCMD) | 17 |  | 1900-01-16 |  |  | Buyers Agent
| Lead Paint Notification, pre-1978 (FLD-11) (if applicable) | 17 |  | 1900-01-16 |  |  | Buyers Agent
| Termite Pest Report (approved receipt) | 17 |  | 1900-01-16 |  |  | Buyers Agent
| Receipt for Reports | 17 |  | 1900-01-16 |  |  | Both Agents
| Verification of Final Walkthrough - VP | 5 Days Prior to COE |  |  |  | -5 | Buyers Agent
Formulas:
Scheduled Contingency Expiration = C8+[Due Date (# of Days)]
SELLER
BUYER

## Listing Agent
Enter Acceptance Date and Due Dates will be calculated by number of days entered in Due Date Column. Enter number of days to close escrow and COE date will be calculated. You may tab between fields or mouse over area and click to change information in a cell. | RPA-CA TRANSACTION TIMELINE WORKSHEET TT170330
Property Address:
Agent Name:
Representing:
| Acceptance Date (mm/dd/yyyy): | 2019-10-31
| Number of days to close escrow: | 45 |  | COE Date: | 2019-12-15
| Item/Action Description | Due Date (# of Days) | Scheduled Contingency Expiration | Date Provided / Ordered | Date Received | Provided by
Seller Provided Disclosures and Reports:
| Escrow Opened | 3 | 2019-11-03 |  |  | Listing Agent
| MLS Agent Detail Printout - signed by Seller | 3 | 2019-11-03 |  |  | Listing Agent
| Representative Capacity Signature Disclosure (Seller) - RCSD-S | 3 | 2019-11-03 |  |  | Listing Agent
| Affiliated Business Arrangement Disclosure | 3 | 2019-11-03 |  |  | Listing Agent
| Transfer Disclosure Statement (TDS-11) | 7 | 2019-11-07 |  |  | Listing Agent
| Seller Property Questionnaire (SPQ) | 7 | 2019-11-07 |  |  | Listing Agent
| Exempt Seller Disclosures - ESD (if no SPQ) | 7 | 2019-11-07 |  |  | Listing Agent
| FIRPTA, QS (Qualified Substiture from Escrow) | 7 | 2019-11-07 |  |  | Listing Agent
| Go over Net Sheet with Seller | 7 | 2019-11-07 |  |  | Listing Agent
| Wood Destroying Pest Inspection Report (if applicable) | 7 | 2019-11-07 |  |  | Listing Agent
| Natural Hazard Disclosure (NHD) | 7 | 2019-11-07 |  |  | Listing Agent
| Earthquake Guide Book & Energy Rating Pamphlet | 7 | 2019-11-07 |  |  | Listing Agent
| Residential Earthquake Questionnaire (pre-1960) | 7 | 2019-11-07 |  |  | Listing Agent
| Water Heater/Smoke Detector Statement (WHSD) | 7 | 2019-11-07 |  |  | Listing Agent
| Water Conserving/Monoxide Notice (WCMD) | 7 | 2019-11-07 |  |  | Listing Agent
| Lead Paint Notification,pre-1978 (FLD) (if applicable) | 7 | 2019-11-07 |  |  | Listing Agent
| Termite Pest Report (if applicable) | 7 | 2019-11-07 |  |  | Listing Agent
| Home Warranty | 17 | 2019-11-17 |  |  | Listing Agent
Buyer Contingency Items (if applicable):
| HOA Common Interest Disclosures | 7 | 2019-11-07 |  |  | Listing Agent
| Inspections Contingency Removal (CR) | 17 | 2019-11-17 |  |  | Both Agents
| Appraisal Contingency Removal (if applicable) | 17 | 2019-11-17 |  |  | Both Agents
| Loan Contingency Removal (if applicable) | 21 | 2019-11-21 |  |  | Both Agents
Buyer MUST Approve, Sign and Release the Following Disclosures:
| Purchase Contract (fully signed) | 3 | 2019-11-03 |  |  | Both Agents
| Counter Offers 1,2,3 (Fully Signed) | 3 | 2019-11-03 |  |  | Both Agents
| Addendums 1,2,3 | 3 | 2019-11-03 |  |  | Both Agents
| Affiliated Business Arrangement Disclosure (for BDH) | 3 | 2019-11-03 |  |  | Both Agents
| Agent Visual Inspection Disclosure - AVID | 7 | 2019-11-07 |  |  | Both Agents
| Statewide Buyer & Seller Advisory (SBSA) | 17 | 2019-11-17 |  |  | Both Agents
| Seller Property Questionnaire (SPQ) | 17 | 2019-11-17 |  |  | Both Agents
| Receipt for Reports | 17 | 2019-11-17 |  |  | Both Agents
Formulas:
Scheduled Contingency Expiration = C8+[Due Date (# of Days)]
SELLER

## Buyers Agent
Enter Acceptance Date and Due Dates will be calculated by number of days entered in Due Date Column. Enter number of days to close escrow and COE date will be calculated. You may tab between fields or mouse over area and click to change information in a cell. | RPA-CA TRANSACTION TIMELINE WORKSHEET TT170330
Property Address:
Agent Name:
Representing:
Acceptance Date (mm/dd/yyyy):
| Number of days to close escrow: |  |  | COE Date: | 0
| Item/Action Description | Due Date (# of Days) | Scheduled Contingency Expiration | Date Provided / Ordered | Date Received | Provided by
Buyer Contingency Items (if applicable):
| Verification of Funds to Close | 3 | 1900-01-02 |  |  | Buyers Agent
| Appraisal Contingency Removal (if applicable) | 17 | 1900-01-16 |  |  | Both Agents
| Loan Contingency Removal (if applicable) | 21 | 1900-01-20 |  |  | Both Agents
| Inspections Contingency Removal (CR) | 17 | 1900-01-16 |  |  | Both Agents
| Home Inspection Report | 17 | 1900-01-16 |  |  | Buyers Agent
| Request for Repairs & Sellers Response - RR & RRRR | 17 | 1900-01-16 |  |  | Buyers Agent
Buyer MUST Approve, Sign and Release the Following Disclosures:
| Purchase Contract (fully signed) | 3 | 1900-01-02 |  |  | Both Agents
| Buyer Representation Agreement (BRNN,BRE,or BRNE) | 3 | 1900-01-02 |  |  | Buyers Agent
| Representative Capacity Signature Disclosure (Buyer) - RCSD-B | 3 | 1900-01-02 |  |  | Buyers Agent
| FHA/VA Notice and Addendum - FVA | 3 | 1900-01-02 |  |  | Buyers Agent
| FHA/VA Amendatory Clause - FHA/VA | 17 | 1900-01-16 |  |  | Buyers Agent
| Counter Offers 1,2,3 (Fully Signed) | 3 | 1900-01-02 |  |  | Both Agents
| Addendums 1,2,3 | 3 | 1900-01-02 |  |  | Both Agents
| Agency Disclosure (Buyers Agent) | with Offer |  |  |  | Buyers Agent
| Market Conditions Advisory (MCA) | 3 | 1900-01-02 |  |  | Buyers Agent
| Affiliated Business Arrangement Disclosure (for BDH) | 3 | 1900-01-02 |  |  | Both Agents
| Buyers Inspection Advisory | with Offer |  |  |  | Buyers Agent
| Ensure Appraisal is Scheduled | 7 | 1900-01-06 |  |  | Buyers Agent
| Transfer Disclosure Statement (TDS) | 17 | 1900-01-16 |  |  | Buyers Agent
| Statewide Buyer & Seller Advisory (SBSA) | 17 | 1900-01-16 |  |  | Both Agents
| Seller Property Questionnaire (SPQ) | 17 | 1900-01-16 |  |  | Both Agents
| Exempt Seller Disclosures - ESD (if no SPQ) | 17 | 1900-01-16 |  |  | Buyers Agent
| Agent Visual Inspection Disclosure - AVID | 7 | 1900-01-06 |  |  | Both Agents
| Leased/liened Items Disclosure | 7 | 1900-01-06 |  |  | Buyers Agent
| NHD & Tax/Mello-Roos page (if applicable) - receipt | 17 | 1900-01-16 |  |  | Buyers Agent
| Earthquake Guide Book (receipt) | 17 | 1900-01-16 |  |  | Buyers Agent
| Water Heater/Smoke Detector Statement (WHSD) | 17 | 1900-01-16 |  |  | Buyers Agent
| Water Conserving/Monoxide Notice (WCMD) | 17 | 1900-01-16 |  |  | Buyers Agent
| Lead Paint Notification, pre-1978 (FLD-11) (if applicable) | 17 | 1900-01-16 |  |  | Buyers Agent
| Termite Pest Report (approved receipt) | 17 | 1900-01-16 |  |  | Buyers Agent
| Receipt for Reports | 17 | 1900-01-16 |  |  | Both Agents
| Verification of Final Walkthrough - VP | 5 Days Prior to COE |  |  | -5 | Buyers Agent
Formulas:
Scheduled Contingency Expiration = C8+[Due Date (# of Days)]
BUYER

## Escrow
Enter Acceptance Date and Due Dates will be calculated by number of days entered in Due Date Column. Enter number of days to close escrow and COE date will be calculated. You may tab between fields or mouse over area and click to change information in a cell. | RPA-CA TRANSACTION TIMELINE WORKSHEET TT170330
Property Address:
Agent Name:
Representing:
Acceptance Date (mm/dd/yyyy):
| Number of days to close escrow: |  |  | COE Date: | 0
| Item/Action Description | Due Date (# of Days) | Scheduled Contingency Expiration | Date Provided / Ordered | Date Received | Provided by
Seller Provided Disclosures and Reports:
| Submit HOA Information Request (If Applicable) | 3 | 1900-01-02 |  |  | Escrow
| Home Owners Assoc. Documents & CCR's | 7 | 1900-01-06 |  |  | Escrow
| Preliminary Title Report | 7 | 1900-01-06 |  |  | Escrow
Buyer MUST Approve, Sign and Release the Following Disclosures:
| Receipt for Deposit | 3 | 1900-01-02 |  |  | Escrow
| Home Owner Association Documents (approval) | 17 | 1900-01-16 |  |  | Escrow
| Preliminary Title Report | 17 | 1900-01-16 |  |  | Escrow
Formulas:
Scheduled Contingency Expiration = C8+[Due Date (# of Days)]
SELLER
BUYER